## 版本5.1.7新特性¦Fix Bug
No | 重要程度 | 紧急程度 | 特性描述 | 版本/类型 | 分类 | 是否解决 | 解决时间 | 是否提交 | 提交时间 | 相关修改文件 | 相关修改人 | 相关项目组 | 测试人 | 验证情况 | 验证通过时间 | 能否上线 | Bug 禅道ID | Bug redmineID | 是否影响数据 | 备注
1 | 重要 | 紧急 | 所有项目Memcached缓存一致性Hash环配置 | New Features | bs,messages,partner,partnerpc,payapi, renter,renterembed,renterpc,tasktracker | 是 | 2016-12-10 | 是 | 2016-12-12 | spring-cache.xml, systemconfig.properties | 九天 | 架构组 | 九天 | 通过 | 2016-12-12 | 能 |  |  | 否 | 自测验证
2 | 重要 | 紧急 | 修复敏感词过滤占用CPU问题 | Fix Bugs | 全部项目 | 是 | 2012-12-12 | 是 | 2012-12-12 |  | 冯银鹏 | 架构组 | [6 empty] | 否
3 | 重要 | 不紧急 | 修正由于业务调整出现的对账误报错误问题 | Fix Bugs | BS | 是 | 2012-12-12 | 是 | 2012-12-12 |  | 田志敏 | 架构组

## 定时器
上线版本 | 任务类型 | 执行节点 | 项目组 | 用途 | 技术经理 | 开发人 | 使用与否 | 可否删除 | 定时器类名称 | Crontab定时任务 | LTS中定时器名称 | LTS中定时器执行参数 | 任务类型 | 周期 | 是否依赖其他job | 执行结果及报错补救方案 | 备注

## 上线执行顺序
5.2.0项目上线准备执行方案 （预发布环境先验证一遍）
顺序编号 | 阶段 | 类型 | 内容 | 注意点 | 负责人 | 是否已完成 | 预计完成时间 | 实际完成时间 | 进展 | 备注

## 配置文件（测试环境）
配置汇总
序号 | 项目组 | 版本号 | 配置所属系统 | 配置文件路径 | 属性 | 配置的详细内容 | 用途 | 环境 | 开发人 | 责任人 | 项目经理 | 备注
1 | 架构组 | 5.1.7 | mogoroom-bs | systemconfig.properties | 新增 | #memcached-server memcached.memClientBiz1.host= memcached.memClientBiz1.port= memcached.memClientBiz1.weight=10 memcached.memClientBiz2.host= memcached.memClientBiz2.port= memcached.memClientBiz2.weight=10 memcached.memClientBiz3.host= memcached.memClientBiz3.port= memcached.memClientBiz3.weight=10 memcached.memClientSearch1.host= memcached.memClientSearch1.port= memcached.memClientSearch1.weight=10 memcached.memClientSearch2.host= memcached.memClientSearch2.port= memcached.memClientSearch2.weight=10 | Memcached 一致性Hash环 配置 | 生产环境 | 九天 | 九天 | 九天 | host,port请根据 实际服务器情况配置
2 | 架构组 | 5.1.7 | mogoroom-messages | systemconfig.properties | 新增 | #memcached-server memcached.memClientBiz1.host= memcached.memClientBiz1.port= memcached.memClientBiz1.weight=10 memcached.memClientBiz2.host= memcached.memClientBiz2.port= memcached.memClientBiz2.weight=10 memcached.memClientBiz3.host= memcached.memClientBiz3.port= memcached.memClientBiz3.weight=10 memcached.memClientSearch1.host= memcached.memClientSearch1.port= memcached.memClientSearch1.weight=10 memcached.memClientSearch2.host= memcached.memClientSearch2.port= memcached.memClientSearch2.weight=10 | Memcached 一致性Hash环 配置 | 生产环境 | 九天 | 九天 | 九天 | host,port请根据 实际服务器情况配置
3 | 架构组 | 5.1.7 | mogoroom-partner | systemconfig.properties | 新增 | #memcached-server memcached.memClientBiz1.host= memcached.memClientBiz1.port= memcached.memClientBiz1.weight=10 memcached.memClientBiz2.host= memcached.memClientBiz2.port= memcached.memClientBiz2.weight=10 memcached.memClientBiz3.host= memcached.memClientBiz3.port= memcached.memClientBiz3.weight=10 memcached.memClientSearch1.host= memcached.memClientSearch1.port= memcached.memClientSearch1.weight=10 memcached.memClientSearch2.host= memcached.memClientSearch2.port= memcached.memClientSearch2.weight=10 | Memcached 一致性Hash环 配置 | 生产环境 | 九天 | 九天 | 九天 | host,port请根据 实际服务器情况配置
4 | 架构组 | 5.1.7 | mogoroom-partnerpc | systemconfig.properties | 新增 | #memcached-server memcached.memClientBiz1.host= memcached.memClientBiz1.port= memcached.memClientBiz1.weight=10 memcached.memClientBiz2.host= memcached.memClientBiz2.port= memcached.memClientBiz2.weight=10 memcached.memClientBiz3.host= memcached.memClientBiz3.port= memcached.memClientBiz3.weight=10 memcached.memClientSearch1.host= memcached.memClientSearch1.port= memcached.memClientSearch1.weight=10 memcached.memClientSearch2.host= memcached.memClientSearch2.port= memcached.memClientSearch2.weight=10 | Memcached 一致性Hash环 配置 | 生产环境 | 九天 | 九天 | 九天 | host,port请根据 实际服务器情况配置
5 | 架构组 | 5.1.7 | mogoroom-payapi | systemconfig.properties | 新增 | #memcached-server memcached.memClientBiz1.host= memcached.memClientBiz1.port= memcached.memClientBiz1.weight=10 memcached.memClientBiz2.host= memcached.memClientBiz2.port= memcached.memClientBiz2.weight=10 memcached.memClientBiz3.host= memcached.memClientBiz3.port= memcached.memClientBiz3.weight=10 memcached.memClientSearch1.host= memcached.memClientSearch1.port= memcached.memClientSearch1.weight=10 memcached.memClientSearch2.host= memcached.memClientSearch2.port= memcached.memClientSearch2.weight=10 | Memcached 一致性Hash环 配置 | 生产环境 | 九天 | 九天 | 九天 | host,port请根据 实际服务器情况配置
6 | 架构组 | 5.1.7 | mogoroom-renter | systemconfig.properties | 新增 | #memcached-server memcached.memClientBiz1.host= memcached.memClientBiz1.port= memcached.memClientBiz1.weight=10 memcached.memClientBiz2.host= memcached.memClientBiz2.port= memcached.memClientBiz2.weight=10 memcached.memClientBiz3.host= memcached.memClientBiz3.port= memcached.memClientBiz3.weight=10 memcached.memClientSearch1.host= memcached.memClientSearch1.port= memcached.memClientSearch1.weight=10 memcached.memClientSearch2.host= memcached.memClientSearch2.port= memcached.memClientSearch2.weight=10 | Memcached 一致性Hash环 配置 | 生产环境 | 九天 | 九天 | 九天 | host,port请根据 实际服务器情况配置
7 | 架构组 | 5.1.7 | mogoroom-renterembed | systemconfig.properties | 新增 | #memcached-server memcached.memClientBiz1.host= memcached.memClientBiz1.port= memcached.memClientBiz1.weight=10 memcached.memClientBiz2.host= memcached.memClientBiz2.port= memcached.memClientBiz2.weight=10 memcached.memClientBiz3.host= memcached.memClientBiz3.port= memcached.memClientBiz3.weight=10 memcached.memClientSearch1.host= memcached.memClientSearch1.port= memcached.memClientSearch1.weight=10 memcached.memClientSearch2.host= memcached.memClientSearch2.port= memcached.memClientSearch2.weight=10 | Memcached 一致性Hash环 配置 | 生产环境 | 九天 | 九天 | 九天 | host,port请根据 实际服务器情况配置
8 | 架构组 | 5.1.7 | mogoroom-renterpc | systemconfig.properties | 新增 | #memcached-server memcached.memClientBiz1.host= memcached.memClientBiz1.port= memcached.memClientBiz1.weight=10 memcached.memClientBiz2.host= memcached.memClientBiz2.port= memcached.memClientBiz2.weight=10 memcached.memClientBiz3.host= memcached.memClientBiz3.port= memcached.memClientBiz3.weight=10 memcached.memClientSearch1.host= memcached.memClientSearch1.port= memcached.memClientSearch1.weight=10 memcached.memClientSearch2.host= memcached.memClientSearch2.port= memcached.memClientSearch2.weight=10 | Memcached 一致性Hash环 配置 | 生产环境 | 九天 | 九天 | 九天 | host,port请根据 实际服务器情况配置
9 | 架构组 | 5.1.7 | mogoroom-tasktracker | systemconfig.properties | 新增 | #memcached-server memcached.memClientBiz1.host= memcached.memClientBiz1.port= memcached.memClientBiz1.weight=10 memcached.memClientBiz2.host= memcached.memClientBiz2.port= memcached.memClientBiz2.weight=10 memcached.memClientBiz3.host= memcached.memClientBiz3.port= memcached.memClientBiz3.weight=10 memcached.memClientSearch1.host= memcached.memClientSearch1.port= memcached.memClientSearch1.weight=10 memcached.memClientSearch2.host= memcached.memClientSearch2.port= memcached.memClientSearch2.weight=10 | Memcached 一致性Hash环 配置 | 生产环境 | 九天 | 九天 | 九天 | host,port请根据 实际服务器情况配置
10 | 架构组 | 5.1.7 | mogoda-tasktracker | systemconfig.properties | 新增 | #memcached-server memcached.memClientBiz1.host= memcached.memClientBiz1.port= memcached.memClientBiz1.weight=10 memcached.memClientBiz2.host= memcached.memClientBiz2.port= memcached.memClientBiz2.weight=10 memcached.memClientBiz3.host= memcached.memClientBiz3.port= memcached.memClientBiz3.weight=10 memcached.memClientSearch1.host= memcached.memClientSearch1.port= memcached.memClientSearch1.weight=10 memcached.memClientSearch2.host= memcached.memClientSearch2.port= memcached.memClientSearch2.weight=10 | Memcached 一致性Hash环 配置 | 生产环境 | 九天 | 九天 | 九天 | host,port请根据 实际服务器情况配置

## 配置文件（预发布环境）
配置汇总
序号 | 项目组 | 版本号 | 配置所属系统 | 配置文件路径 | 属性 | 配置的详细内容 | 用途 | 环境 | 开发人 | 责任人 | 项目经理 | 备注
1 | 架构组 | 5.1.7 | mogoroom-bs | systemconfig.properties | 新增 | #memcached-server memcached.memClientBiz1.host= memcached.memClientBiz1.port= memcached.memClientBiz1.weight=10 memcached.memClientBiz2.host= memcached.memClientBiz2.port= memcached.memClientBiz2.weight=10 memcached.memClientBiz3.host= memcached.memClientBiz3.port= memcached.memClientBiz3.weight=10 memcached.memClientSearch1.host= memcached.memClientSearch1.port= memcached.memClientSearch1.weight=10 memcached.memClientSearch2.host= memcached.memClientSearch2.port= memcached.memClientSearch2.weight=10 | Memcached 一致性Hash环 配置 | 生产环境 | 九天 | 九天 | 九天 | host,port请根据 实际服务器情况配置
2 | 架构组 | 5.1.7 | mogoroom-messages | systemconfig.properties | 新增 | #memcached-server memcached.memClientBiz1.host= memcached.memClientBiz1.port= memcached.memClientBiz1.weight=10 memcached.memClientBiz2.host= memcached.memClientBiz2.port= memcached.memClientBiz2.weight=10 memcached.memClientBiz3.host= memcached.memClientBiz3.port= memcached.memClientBiz3.weight=10 memcached.memClientSearch1.host= memcached.memClientSearch1.port= memcached.memClientSearch1.weight=10 memcached.memClientSearch2.host= memcached.memClientSearch2.port= memcached.memClientSearch2.weight=10 | Memcached 一致性Hash环 配置 | 生产环境 | 九天 | 九天 | 九天 | host,port请根据 实际服务器情况配置
3 | 架构组 | 5.1.7 | mogoroom-partner | systemconfig.properties | 新增 | #memcached-server memcached.memClientBiz1.host= memcached.memClientBiz1.port= memcached.memClientBiz1.weight=10 memcached.memClientBiz2.host= memcached.memClientBiz2.port= memcached.memClientBiz2.weight=10 memcached.memClientBiz3.host= memcached.memClientBiz3.port= memcached.memClientBiz3.weight=10 memcached.memClientSearch1.host= memcached.memClientSearch1.port= memcached.memClientSearch1.weight=10 memcached.memClientSearch2.host= memcached.memClientSearch2.port= memcached.memClientSearch2.weight=10 | Memcached 一致性Hash环 配置 | 生产环境 | 九天 | 九天 | 九天 | host,port请根据 实际服务器情况配置
4 | 架构组 | 5.1.7 | mogoroom-partnerpc | systemconfig.properties | 新增 | #memcached-server memcached.memClientBiz1.host= memcached.memClientBiz1.port= memcached.memClientBiz1.weight=10 memcached.memClientBiz2.host= memcached.memClientBiz2.port= memcached.memClientBiz2.weight=10 memcached.memClientBiz3.host= memcached.memClientBiz3.port= memcached.memClientBiz3.weight=10 memcached.memClientSearch1.host= memcached.memClientSearch1.port= memcached.memClientSearch1.weight=10 memcached.memClientSearch2.host= memcached.memClientSearch2.port= memcached.memClientSearch2.weight=10 | Memcached 一致性Hash环 配置 | 生产环境 | 九天 | 九天 | 九天 | host,port请根据 实际服务器情况配置
5 | 架构组 | 5.1.7 | mogoroom-payapi | systemconfig.properties | 新增 | #memcached-server memcached.memClientBiz1.host= memcached.memClientBiz1.port= memcached.memClientBiz1.weight=10 memcached.memClientBiz2.host= memcached.memClientBiz2.port= memcached.memClientBiz2.weight=10 memcached.memClientBiz3.host= memcached.memClientBiz3.port= memcached.memClientBiz3.weight=10 memcached.memClientSearch1.host= memcached.memClientSearch1.port= memcached.memClientSearch1.weight=10 memcached.memClientSearch2.host= memcached.memClientSearch2.port= memcached.memClientSearch2.weight=10 | Memcached 一致性Hash环 配置 | 生产环境 | 九天 | 九天 | 九天 | host,port请根据 实际服务器情况配置
6 | 架构组 | 5.1.7 | mogoroom-renter | systemconfig.properties | 新增 | #memcached-server memcached.memClientBiz1.host= memcached.memClientBiz1.port= memcached.memClientBiz1.weight=10 memcached.memClientBiz2.host= memcached.memClientBiz2.port= memcached.memClientBiz2.weight=10 memcached.memClientBiz3.host= memcached.memClientBiz3.port= memcached.memClientBiz3.weight=10 memcached.memClientSearch1.host= memcached.memClientSearch1.port= memcached.memClientSearch1.weight=10 memcached.memClientSearch2.host= memcached.memClientSearch2.port= memcached.memClientSearch2.weight=10 | Memcached 一致性Hash环 配置 | 生产环境 | 九天 | 九天 | 九天 | host,port请根据 实际服务器情况配置
7 | 架构组 | 5.1.7 | mogoroom-renterembed | systemconfig.properties | 新增 | #memcached-server memcached.memClientBiz1.host= memcached.memClientBiz1.port= memcached.memClientBiz1.weight=10 memcached.memClientBiz2.host= memcached.memClientBiz2.port= memcached.memClientBiz2.weight=10 memcached.memClientBiz3.host= memcached.memClientBiz3.port= memcached.memClientBiz3.weight=10 memcached.memClientSearch1.host= memcached.memClientSearch1.port= memcached.memClientSearch1.weight=10 memcached.memClientSearch2.host= memcached.memClientSearch2.port= memcached.memClientSearch2.weight=10 | Memcached 一致性Hash环 配置 | 生产环境 | 九天 | 九天 | 九天 | host,port请根据 实际服务器情况配置
8 | 架构组 | 5.1.7 | mogoroom-renterpc | systemconfig.properties | 新增 | #memcached-server memcached.memClientBiz1.host= memcached.memClientBiz1.port= memcached.memClientBiz1.weight=10 memcached.memClientBiz2.host= memcached.memClientBiz2.port= memcached.memClientBiz2.weight=10 memcached.memClientBiz3.host= memcached.memClientBiz3.port= memcached.memClientBiz3.weight=10 memcached.memClientSearch1.host= memcached.memClientSearch1.port= memcached.memClientSearch1.weight=10 memcached.memClientSearch2.host= memcached.memClientSearch2.port= memcached.memClientSearch2.weight=10 | Memcached 一致性Hash环 配置 | 生产环境 | 九天 | 九天 | 九天 | host,port请根据 实际服务器情况配置
9 | 架构组 | 5.1.7 | mogoroom-tasktracker | systemconfig.properties | 新增 | #memcached-server memcached.memClientBiz1.host= memcached.memClientBiz1.port= memcached.memClientBiz1.weight=10 memcached.memClientBiz2.host= memcached.memClientBiz2.port= memcached.memClientBiz2.weight=10 memcached.memClientBiz3.host= memcached.memClientBiz3.port= memcached.memClientBiz3.weight=10 memcached.memClientSearch1.host= memcached.memClientSearch1.port= memcached.memClientSearch1.weight=10 memcached.memClientSearch2.host= memcached.memClientSearch2.port= memcached.memClientSearch2.weight=10 | Memcached 一致性Hash环 配置 | 生产环境 | 九天 | 九天 | 九天 | host,port请根据 实际服务器情况配置
10 | 架构组 | 5.1.7 | mogoda-tasktracker | systemconfig.properties | 新增 | #memcached-server memcached.memClientBiz1.host= memcached.memClientBiz1.port= memcached.memClientBiz1.weight=10 memcached.memClientBiz2.host= memcached.memClientBiz2.port= memcached.memClientBiz2.weight=10 memcached.memClientBiz3.host= memcached.memClientBiz3.port= memcached.memClientBiz3.weight=10 memcached.memClientSearch1.host= memcached.memClientSearch1.port= memcached.memClientSearch1.weight=10 memcached.memClientSearch2.host= memcached.memClientSearch2.port= memcached.memClientSearch2.weight=10 | Memcached 一致性Hash环 配置 | 生产环境 | 九天 | 九天 | 九天 | host,port请根据 实际服务器情况配置

## 配置文件（生产环境）
配置汇总
序号 | 项目组 | 版本号 | 配置所属系统 | 配置文件路径 | 属性 | 配置的详细内容 | 用途 | 环境 | 开发人 | 责任人 | 项目经理 | 备注
1 | 架构组 | 5.1.7 | mogoroom-bs | systemconfig.properties | 新增 | #memcached-server memcached.memClientBiz1.host= memcached.memClientBiz1.port= memcached.memClientBiz1.weight=10 memcached.memClientBiz2.host= memcached.memClientBiz2.port= memcached.memClientBiz2.weight=10 memcached.memClientBiz3.host= memcached.memClientBiz3.port= memcached.memClientBiz3.weight=10 memcached.memClientSearch1.host= memcached.memClientSearch1.port= memcached.memClientSearch1.weight=10 memcached.memClientSearch2.host= memcached.memClientSearch2.port= memcached.memClientSearch2.weight=10 | Memcached 一致性Hash环 配置 | 生产环境 | 九天 | 九天 | 九天 | host,port请运维根据 实际服务器情况配置
2 | 架构组 | 5.1.7 | mogoroom-messages | systemconfig.properties | 新增 | #memcached-server memcached.memClientBiz1.host= memcached.memClientBiz1.port= memcached.memClientBiz1.weight=10 memcached.memClientBiz2.host= memcached.memClientBiz2.port= memcached.memClientBiz2.weight=10 memcached.memClientBiz3.host= memcached.memClientBiz3.port= memcached.memClientBiz3.weight=10 memcached.memClientSearch1.host= memcached.memClientSearch1.port= memcached.memClientSearch1.weight=10 memcached.memClientSearch2.host= memcached.memClientSearch2.port= memcached.memClientSearch2.weight=10 | Memcached 一致性Hash环 配置 | 生产环境 | 九天 | 九天 | 九天 | host,port请运维根据 实际服务器情况配置
3 | 架构组 | 5.1.7 | mogoroom-partner | systemconfig.properties | 新增 | #memcached-server memcached.memClientBiz1.host= memcached.memClientBiz1.port= memcached.memClientBiz1.weight=10 memcached.memClientBiz2.host= memcached.memClientBiz2.port= memcached.memClientBiz2.weight=10 memcached.memClientBiz3.host= memcached.memClientBiz3.port= memcached.memClientBiz3.weight=10 memcached.memClientSearch1.host= memcached.memClientSearch1.port= memcached.memClientSearch1.weight=10 memcached.memClientSearch2.host= memcached.memClientSearch2.port= memcached.memClientSearch2.weight=10 | Memcached 一致性Hash环 配置 | 生产环境 | 九天 | 九天 | 九天 | host,port请运维根据 实际服务器情况配置
4 | 架构组 | 5.1.7 | mogoroom-partnerpc | systemconfig.properties | 新增 | #memcached-server memcached.memClientBiz1.host= memcached.memClientBiz1.port= memcached.memClientBiz1.weight=10 memcached.memClientBiz2.host= memcached.memClientBiz2.port= memcached.memClientBiz2.weight=10 memcached.memClientBiz3.host= memcached.memClientBiz3.port= memcached.memClientBiz3.weight=10 memcached.memClientSearch1.host= memcached.memClientSearch1.port= memcached.memClientSearch1.weight=10 memcached.memClientSearch2.host= memcached.memClientSearch2.port= memcached.memClientSearch2.weight=10 | Memcached 一致性Hash环 配置 | 生产环境 | 九天 | 九天 | 九天 | host,port请运维根据 实际服务器情况配置
5 | 架构组 | 5.1.7 | mogoroom-payapi | systemconfig.properties | 新增 | #memcached-server memcached.memClientBiz1.host= memcached.memClientBiz1.port= memcached.memClientBiz1.weight=10 memcached.memClientBiz2.host= memcached.memClientBiz2.port= memcached.memClientBiz2.weight=10 memcached.memClientBiz3.host= memcached.memClientBiz3.port= memcached.memClientBiz3.weight=10 memcached.memClientSearch1.host= memcached.memClientSearch1.port= memcached.memClientSearch1.weight=10 memcached.memClientSearch2.host= memcached.memClientSearch2.port= memcached.memClientSearch2.weight=10 | Memcached 一致性Hash环 配置 | 生产环境 | 九天 | 九天 | 九天 | host,port请运维根据 实际服务器情况配置
6 | 架构组 | 5.1.7 | mogoroom-renter | systemconfig.properties | 新增 | #memcached-server memcached.memClientBiz1.host= memcached.memClientBiz1.port= memcached.memClientBiz1.weight=10 memcached.memClientBiz2.host= memcached.memClientBiz2.port= memcached.memClientBiz2.weight=10 memcached.memClientBiz3.host= memcached.memClientBiz3.port= memcached.memClientBiz3.weight=10 memcached.memClientSearch1.host= memcached.memClientSearch1.port= memcached.memClientSearch1.weight=10 memcached.memClientSearch2.host= memcached.memClientSearch2.port= memcached.memClientSearch2.weight=10 | Memcached 一致性Hash环 配置 | 生产环境 | 九天 | 九天 | 九天 | host,port请运维根据 实际服务器情况配置
7 | 架构组 | 5.1.7 | mogoroom-renterembed | systemconfig.properties | 新增 | #memcached-server memcached.memClientBiz1.host= memcached.memClientBiz1.port= memcached.memClientBiz1.weight=10 memcached.memClientBiz2.host= memcached.memClientBiz2.port= memcached.memClientBiz2.weight=10 memcached.memClientBiz3.host= memcached.memClientBiz3.port= memcached.memClientBiz3.weight=10 memcached.memClientSearch1.host= memcached.memClientSearch1.port= memcached.memClientSearch1.weight=10 memcached.memClientSearch2.host= memcached.memClientSearch2.port= memcached.memClientSearch2.weight=10 | Memcached 一致性Hash环 配置 | 生产环境 | 九天 | 九天 | 九天 | host,port请运维根据 实际服务器情况配置
8 | 架构组 | 5.1.7 | mogoroom-renterpc | systemconfig.properties | 新增 | #memcached-server memcached.memClientBiz1.host= memcached.memClientBiz1.port= memcached.memClientBiz1.weight=10 memcached.memClientBiz2.host= memcached.memClientBiz2.port= memcached.memClientBiz2.weight=10 memcached.memClientBiz3.host= memcached.memClientBiz3.port= memcached.memClientBiz3.weight=10 memcached.memClientSearch1.host= memcached.memClientSearch1.port= memcached.memClientSearch1.weight=10 memcached.memClientSearch2.host= memcached.memClientSearch2.port= memcached.memClientSearch2.weight=10 | Memcached 一致性Hash环 配置 | 生产环境 | 九天 | 九天 | 九天 | host,port请运维根据 实际服务器情况配置
9 | 架构组 | 5.1.7 | mogoroom-tasktracker | systemconfig.properties | 新增 | #memcached-server memcached.memClientBiz1.host= memcached.memClientBiz1.port= memcached.memClientBiz1.weight=10 memcached.memClientBiz2.host= memcached.memClientBiz2.port= memcached.memClientBiz2.weight=10 memcached.memClientBiz3.host= memcached.memClientBiz3.port= memcached.memClientBiz3.weight=10 memcached.memClientSearch1.host= memcached.memClientSearch1.port= memcached.memClientSearch1.weight=10 memcached.memClientSearch2.host= memcached.memClientSearch2.port= memcached.memClientSearch2.weight=10 | Memcached 一致性Hash环 配置 | 生产环境 | 九天 | 九天 | 九天 | host,port请运维根据 实际服务器情况配置
10 | 架构组 | 5.1.7 | mogoda-tasktracker | systemconfig.properties | 新增 | #memcached-server memcached.memClientBiz1.host= memcached.memClientBiz1.port= memcached.memClientBiz1.weight=10 memcached.memClientBiz2.host= memcached.memClientBiz2.port= memcached.memClientBiz2.weight=10 memcached.memClientBiz3.host= memcached.memClientBiz3.port= memcached.memClientBiz3.weight=10 memcached.memClientSearch1.host= memcached.memClientSearch1.port= memcached.memClientSearch1.weight=10 memcached.memClientSearch2.host= memcached.memClientSearch2.port= memcached.memClientSearch2.weight=10 | Memcached 一致性Hash环 配置 | 生产环境 | 九天 | 九天 | 九天 | host,port请运维根据 实际服务器情况配置

## 配置文件（公测环境）
配置汇总
序号 | 项目组 | 版本号 | 配置所属系统 | 配置文件路径 | 属性 | 配置的详细内容 | 用途 | 环境 | 开发人 | 责任人 | 项目经理 | 备注

## 数据修复
对应backlog序号 | bug描述 | 影响数据范围 | 影响级别 | 是否修正 | 预计修正时间 | 修正的方式（是脚本修复还是功能工具修复） | 修正负责人